## Sheet1
Bug ID	Product	Component	Assignee	Status	Resolution	Summary	Changed
118671	Impress	viewing	issues@openoffice.apache.org	CONFIRMED	---	Simple macro crashes OOo.Impress	06/06/13 10:16 AM
118936	General	security	issues@openoffice.apache.org	CONFIRMED	---	Can't open xlsx(2007-2010) file with password	06/06/13 08:35 AM
118986	Writer	save-export	issues@openoffice.apache.org	CONFIRMED	---	[RTF export] crashes when copy an empty line from Writer below a tif picture then paste into spreadsheet	06/06/13 06:37 AM
119152	General	security	security@openoffice.apache.org	CONFIRMED	---	creating seperating temp files for images for password protected document (if contains images)	06/06/13 08:35 AM
119163	Installation	code	issues@openoffice.apache.org	CONFIRMED	---	Dulicated open with entries for files with OLE after I upgrade to AOO 3.4 Rev r1303653 on Windows XP	06/06/13 08:41 AM
119164	Installation	code	issues@openoffice.apache.org	CONFIRMED	---	File extension association doesn't work after I install other ODF editor and then upgrade to AOO 3.4	06/06/13 08:41 AM
119218	Installation	ui	issues@openoffice.apache.org	CONFIRMED	---	Upgrade from English full package to Simplified Langauge package, the UI is kept English and the witch language couldn't work	06/06/13 08:42 AM
119341	performance	www	issues@openoffice.apache.org	CONFIRMED	---	Worse than Linear Performance Degradation with Tracked-Changes Growth	06/06/13 08:42 AM
119433	Impress	open-import	issues@openoffice.apache.org	CONFIRMED	---	PPT Import: the AOO Impress crash when open .ppt file	06/06/13 06:37 AM
119798	Impress	code	issues@openoffice.apache.org	CONFIRMED	---	Crash occurs when opening attached ppt in AOO3.4.	06/06/13 06:37 AM
119919	Writer	ui	issues@openoffice.apache.org	CONFIRMED	---	[From Symphony][Crash]When press "Ctrl+Shift+Backspace" in table cell "A1" ,Undo,crash	06/06/13 06:37 AM
119935	General	scripting	issues@openoffice.apache.org	CONFIRMED	---	private:stream - load component from ByteArray crashes aoo34	06/06/13 06:37 AM
119946	Build Tools	solenv	issues@openoffice.apache.org	CONFIRMED	---	[Windows 8 certification]Windows App Certification Kit - Test for "Section 3 Apps support Windows security features" is failed.	06/06/13 08:44 AM
119947	General	ui	issues@openoffice.apache.org	CONFIRMED	---	[Windows 8 certification]Windows App Certification Kit - Test for "Section 4 Apps must adhere to system restart manager messages" is failed	06/06/13 08:45 AM
119957	Writer	editing	jsc@apache.org	CONFIRMED	---	[From Symphony]Application crashed if undo paste text from shape	06/06/13 08:44 AM
119995	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	Calc crashed if click formula toolbar while range picker enabled in another calc document	06/06/13 08:45 AM
120007	Writer	formatting	issues@openoffice.apache.org	CONFIRMED	---	Repeated crashing when formatting in text box	06/06/13 09:33 AM
120020	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	Application crash when undo "Ctrl+Delete" under "Outline" view in SD.	06/06/13 09:33 AM
120023	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	[Regression]Copy and Paste from OO Text doc to Spreadsheet on OO V3.4	06/06/13 09:33 AM
120115	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	unconformant DOCX silently crashes on opening	06/06/13 09:33 AM
120144	Impress	ui	issues@openoffice.apache.org	CONFIRMED	---	[Regression]the date is still shown on the first slide when switch to slide sorter view.	06/06/13 09:34 AM
120216	Calc	save-export	issues@openoffice.apache.org	CONFIRMED	---	Save as csv, tab separated isn't possible	06/06/13 08:46 AM
120222	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	[Regression]Select all sheets, then click any sheet tab which is not the current focused sheet, the selection will be cancelled.	06/06/13 09:33 AM
120245	Writer	formatting	issues@openoffice.apache.org	CONFIRMED	---	Typed in latest version of openoffice on windows in Arabic, saved file as .odt, opened in latest version of openoffice on my mac to print the document to see that the words are not in arabic but only the letters are.	06/06/13 08:47 AM
120250	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	Crash while opening RTF file	06/06/13 09:34 AM
120291	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	OpenOffice crashes when opening a RTF file	06/06/13 09:34 AM
120310	General	code	issues@openoffice.apache.org	CONFIRMED	---	testtools bridge test crash on polymorphic struct types	06/06/13 10:08 AM
120335	General	security	security@openoffice.apache.org	CONFIRMED	---	Password for protecting contents is not working properly	06/06/13 08:34 AM
120381	Writer	viewing	issues@openoffice.apache.org	CONFIRMED	---	Viewing any document shows that all words need correction. This condition was not present the last time I saved the document	06/06/13 08:48 AM
120441	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	[Freeze]With data range picker shrink in first document, AOO frozen if switch focus back from another SC doc	06/06/13 08:48 AM
120443	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	The error message:component(com.sun.star.plugin.PluginManager)could not be loader while inserting plug-in	06/06/13 08:48 AM
120446	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	[Freeze]Presentation Freeze while Inserting *.mp3 file type	06/06/13 08:51 AM
120460	Calc	open-import	issues@openoffice.apache.org	CONFIRMED	---	[non-pro] crash in import of special sheet with connectors but empty apart from that	06/06/13 10:08 AM
120513	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Writer crashes in Edit>Changes>Rec-mode on Insert>Comment	06/06/13 09:34 AM
120566	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	[Regression]Select multiple slide don't display delete slide funtion on Win7&Mac,but display well on Ubuntu 10.4	06/06/13 08:22 AM
120588	General	security	security@openoffice.apache.org	CONFIRMED	---	virus infection	06/06/13 08:34 AM
120590	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	[data loss] Chart data will lose after copy/cut chart from moved sheet	06/06/13 08:52 AM
120606	Installation	code	issues@openoffice.apache.org	CONFIRMED	---	Pre-registered extensions are not installed	06/06/13 08:52 AM
120626	Impress	formatting	issues@openoffice.apache.org	CONFIRMED	---	[Crash] OO crash when openning number&bullet odp sample file	06/06/13 10:07 AM
120720	Calc	open-import	issues@openoffice.apache.org	CONFIRMED	---	Import .xls created by Excel 2007, with named drawing object, there is a crash.	06/06/13 08:53 AM
120980	qa	tcm	issues@openoffice.apache.org	CONFIRMED	---	All moduals crash	06/06/13 08:33 AM
121008	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	[crash]Ctrl+Z twice after merged cells, AOO will crash	06/06/13 10:07 AM
121012	Impress	save-export	issues@openoffice.apache.org	CONFIRMED	---	AOO crash when save the odp file into .ppt	06/06/13 09:34 AM
121020	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	Mac:Copy past not work on Mac for Outline	06/06/13 08:20 AM
121062	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	[From Symphony]It will lead AOO freeze when select all cells in spreadsheet and paste the copied cells	06/06/13 08:33 AM
121094	Calc	open-import	issues@openoffice.apache.org	CONFIRMED	---	Calc repeatedly crashes	06/06/13 10:16 AM
121112	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	AOO crash when save the 2007 docx sample which is including tracking change,table,field,picture to odt	06/06/13 09:34 AM
121118	Writer	save-export	issues@openoffice.apache.org	CONFIRMED	---	when export the sample file to pdf from odt,AOO crash.	06/06/13 09:34 AM
121121	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	AOO crash and pop up a recovery dialog when open these doc/docx sample file with OO.	06/06/13 09:34 AM
121125	Writer	code	issues@openoffice.apache.org	CONFIRMED	---	Writer Crashed When 0 Pages Selected for Export as PDF	06/06/13 10:15 AM
121127	Writer	save-export	issues@openoffice.apache.org	CONFIRMED	---	Writer crashes exporting this document to PDF	06/06/13 10:14 AM
121188	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	[non-pro] Crash with Undo immediately after insert new slide	06/06/13 10:06 AM
121256	Impress	save-export	issues@openoffice.apache.org	CONFIRMED	---	Crash when saving ppt on Linux.	06/06/13 10:05 AM
121277	Calc	editing	issues@openoffice.apache.org	CONFIRMED	---	Calc crashes while generating a diagram	06/06/13 10:14 AM
121284	General	code	issues@openoffice.apache.org	CONFIRMED	---	Version Python 2.3.5 is an regression under MacOsX	06/06/13 10:14 AM
121300	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	"Find & Replace" dialog strange behavior (crash)	06/06/13 10:14 AM
121302	Calc	formatting	issues@openoffice.apache.org	CONFIRMED	---	AOO Calc crash when autofilter	06/06/13 08:32 AM
121356	Impress	open-import	issues@openoffice.apache.org	CONFIRMED	---	Crash when loading pptx file second/third time after deleting user installation directory.	06/06/13 10:05 AM
121378	Writer	save-export	issues@openoffice.apache.org	CONFIRMED	---	persistent Save crash event DURING save	06/06/13 10:13 AM
121403	qa	tcm	issues@openoffice.apache.org	CONFIRMED	---	[QA Task]AOO 4.0 milestone regression test execution task	06/06/13 10:13 AM
121417	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	[Automation][Regression]Page number can not be updated correctly until you moved the document. linux32 only.	06/06/13 09:44 AM
121435	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Writer crashes while editing text using filtered "recorded changes" list	06/06/13 10:12 AM
121454	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Problem with "undo" feature on auto-bullet while using "record changes" feature	06/06/13 08:32 AM
121475	Build Tools	external prerequisites	issues@openoffice.apache.org	CONFIRMED	---	Install hangs during "Computing Space Requirements"	06/06/13 08:16 AM
121479	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	RTF file does not open and OOo crashes.	06/06/13 10:12 AM
121554	Writer	code	issues@openoffice.apache.org	CONFIRMED	---	[NON-PRO] Crash drawing text	06/06/13 09:44 AM
121631	Calc	open-import	issues@openoffice.apache.org	CONFIRMED	---	REGRESSION: FILEOPEN particular xml file from Birt Report could be opened only if Java is installed and "Use Java runtime environment" is enabled	06/06/13 10:11 AM
121682	General	ui	issues@openoffice.apache.org	CONFIRMED	---	Problem opening network files	06/06/13 08:31 AM
121751	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	crash after undo language change	06/06/13 10:11 AM
121761	ui	AccessBridge	issues@openoffice.apache.org	CONFIRMED	---	[ia2] Writer crashes on exit with an msvcrt runtime error	06/06/13 09:43 AM
121880	General	ui	issues@openoffice.apache.org	CONFIRMED	---	Find and Replace fails unless case is matched	06/06/13 08:13 AM
121917	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Crash when editing a drawing object anchored to header paragraph	06/06/13 10:11 AM
121925	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Crash when Crtl+Shift+Del at end of table	06/06/13 09:43 AM
121962	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Endless loop with regular expression search	06/06/13 08:29 AM
121968	Installation	ui	issues@openoffice.apache.org	CONFIRMED	---	Installation of AOO 4.0 is not an update of previous versions	06/06/13 08:06 AM
121977	Writer	open-import	issues@openoffice.apache.org	CONFIRMED	---	crash on doc file opening	06/06/13 10:11 AM
121999	Impress	code	issues@openoffice.apache.org	CONFIRMED	---	Click [Slide Sorter] tab and OpenOffice crashes	06/06/13 08:29 AM
122163	Native-Lang	no	issues@openoffice.apache.org	CONFIRMED	---	Print dialog too wide in Norwegian	05/21/13 07:07 PM
122197	Writer	formatting	issues@openoffice.apache.org	CONFIRMED	---	Tag "justify" in Writer/web	06/06/13 08:24 AM
122295	Calc	ui	issues@openoffice.apache.org	CONFIRMED	---	HELP missing for newly implemented functions AVERAGEIF, AVERAGEIFS, SUMIFS, COUNTIFS	05/21/13 02:49 PM
122300	General	code	issues@openoffice.apache.org	CONFIRMED	---	Update the README file	05/19/13 04:16 PM
122312	General	ui	issues@openoffice.apache.org	CONFIRMED	---	Translate content in extras	05/21/13 09:35 PM
122331	Installation	ui	issues@openoffice.apache.org	CONFIRMED	---	first installation dialog "OpenOffice 4.0.0 Installation Preparation" misses application image	05/17/13 11:14 AM
122379	General	ui	issues@openoffice.apache.org	CONFIRMED	---	[sidebar] regression in cursor navigation of some content panel toolbars closing toolbar rather than moving focus for selection	06/06/13 09:41 AM
122414	General	legal	robweir@apache.org	CONFIRMED	---	Need to add IBM copyright to NOTICE file	06/06/13 07:08 AM
122435	Installation	ui	issues@openoffice.apache.org	CONFIRMED	---	CRASH at first launch	06/06/13 09:40 AM
122453	Impress	code	issues@openoffice.apache.org	CONFIRMED	---	[Sidebar] Position and size section not visible when OLE objects inserted.	06/06/13 03:22 AM
122457	Native-Lang	es	jsc@apache.org	CONFIRMED	---	[ES]Integrate last Spanish 4.0 translation	06/05/13 06:03 AM
122481	Writer	editing	issues@openoffice.apache.org	CONFIRMED	---	Typing character in outline causes crash	06/06/13 10:25 AM
122485	Impress	editing	issues@openoffice.apache.org	CONFIRMED	---	[Crash]OOO crash when apply animation for table/chart object	06/06/13 09:40 AM