## Chart (hidden)
Project
Team Member | Chal Haat Haat | ShowDown | Jasn Josh Ka | Mahotsav | Jodi No. 1 | Under Process | Pending | Completed
Rohan | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Sahil | 0 | 4 | 0 | 0 | 0 | 2 | 1 | 1
Deepak | 0 | 0 | 4 | 0 | 0 | 2 | 1 | 1
Priya | 0 | 0 | 0 | 4 | 0 | 2 | 1 | 1
Reshma | 0 | 0 | 0 | 0 | 4 | 1 | 3 | 0
| Team |  |  |  |  | Week
Project | Rohan | Sahil | Deepak | Priya | Reshma | 1 | 2 | 3 | 4
Chal Haat Haat | 4 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
ShowDown | 0 | 4 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Jasn Josh Ka | 0 | 0 | 4 | 0 | 0 | 1 | 1 | 1 | 1
Mahotsav | 0 | 0 | 0 | 4 | 0 | 1 | 1 | 1 | 1
Jodi No. 1 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 1 | 1

## Work (hidden)
# | Team_mem | Project_held | Activity | Status | Week
1 | Rohan | Chal Haat Haat | Findout what to do | Pending | 1
2 | Sahil | ShowDown | Sit and design | Pending | 1
3 | Deepak | Jasn Josh Ka | Findout what to do | Pending | 1
4 | Priya | Mahotsav | Start coding | Pending | 1
5 | Reshma | Jodi No. 1 | Findout what to do | Pending | 1
6 | Rohan | Chal Haat Haat | Sit and design | Pending | 2
7 | Sahil | ShowDown | Update design | Completed | 2
8 | Deepak | Jasn Josh Ka | Sit and design | Under Process | 2
9 | Priya | Mahotsav | Start coding | Completed | 2
10 | Reshma | Jodi No. 1 | Update design | Under Process | 2
11 | Rohan | Chal Haat Haat | Update design | Pending | 3
12 | Sahil | ShowDown | Start coding | Under Process | 3
13 | Deepak | Jasn Josh Ka | Start coding | Completed | 3
14 | Priya | Mahotsav | Update design | Under Process | 3
15 | Reshma | Jodi No. 1 | Start coding | Pending | 3
16 | Rohan | Chal Haat Haat | Flag off | Pending | 4
17 | Sahil | ShowDown | Flag off | Under Process | 4
18 | Deepak | Jasn Josh Ka | Start coding | Under Process | 4
19 | Priya | Mahotsav | Start coding | Under Process | 4
20 | Reshma | Jodi No. 1 | Flag off | Pending | 4

## Legend (hidden)
Team | Project | Activity | Status
Rohan | Chal Haat Haat | Findout what to do | Completed
Sahil | ShowDown | Sit and design | Pending
Deepak | Jasn Josh Ka | Update design | Under Process
Priya | Mahotsav | Start coding
Reshma | Jodi No. 1 | Flag off

## Master
Project | Team | Total Days | Start Date | End Date | Report Received | Activity Days | Rank | Remaing Report | Status
Project-1 | Rohan | 30 | 2010-11-01 | 2010-11-30 | 2010-11-24 | 24 | C | 6 | Pending
Project-2 | Sahil | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-3 | Deepak | 35 | 2010-11-01 | 2010-12-05 | 2010-12-03 | 33 | B | 2 | Under Process
Project-4 | Priya | 30 | 2010-11-01 | 2010-11-30 | 2010-11-05 | 5 | D | 25 | Too Late
Project-5 | Reshu | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-6 | Reshma | 30 | 2010-11-01 | 2010-11-30 | 2010-11-20 | 20 | C | 10 | Pending
Project-7 | Dinesh | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-8 | Kishan | 35 | 2010-11-01 | 2010-12-05 | 2010-11-19 | 19 | D | 16 | Too Late
Project-9 | Kamal | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-10 | Anand | 25 | 2010-11-01 | 2010-11-25 | 2010-11-20 | 20 | B | 5 | Under Process
Project-11 | Rekha | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Project-12 | Bhimsen | 30 | 2010-11-01 | 2010-11-30 | 2010-11-20 | 20 | C | 10 | Pending
Project-13 | Vijaya | 35 | 2010-11-01 | 2010-12-05 | 2010-11-25 | 25 | C | 10 | Pending
Project-14 | Vamsi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-15 | Arun | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-16 | Sudhir | 25 | 2010-11-01 | 2010-11-25 | 2010-11-20 | 20 | B | 5 | Under Process
Project-17 | Meghna | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Project-18 | Prashant | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-19 | Sunil | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-20 | Vivek | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-21 | Nagesh | 35 | 2010-11-01 | 2010-12-05 | 2010-11-25 | 25 | C | 10 | Pending
Project-22 | Ritesh | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-23 | Aarti | 30 | 2010-11-01 | 2010-11-30 | 2010-11-23 | 23 | C | 7 | Pending
Project-24 | Sunita | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-25 | Limsi | 25 | 2010-11-01 | 2010-11-25 | 2010-11-15 | 15 | C | 10 | Pending
Project-26 | Karunakar | 30 | 2010-11-01 | 2010-11-30 | 2010-11-15 | 15 | D | 15 | Too Late
Project-27 | Tarun | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-28 | Mohit | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-29 | Rizvi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-19 | 19 | D | 11 | Too Late
Project-30 | Sanjana | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Project-31 | Suman | 45 | 2010-11-01 | 2010-12-15 | 2010-11-20 | 20 | D | 25 | Too Late
Project-32 | Ranjana | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-33 | Jugnu | 30 | 2010-11-01 | 2010-11-30 | 2010-11-20 | 20 | C | 10 | Pending
Project-34 | Avdesh | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-35 | Satya | 35 | 2010-11-01 | 2010-12-05 | 2010-11-20 | 20 | D | 15 | Too Late
Project-36 | Omi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-37 | Siddharth | 35 | 2010-11-01 | 2010-12-05 | 2010-11-20 | 20 | D | 15 | Too Late
Project-38 | Rinku | 25 | 2010-11-01 | 2010-11-25 | 2010-11-20 | 20 | B | 5 | Under Process
Project-39 | Tulsi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-40 | Slok | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Project-41 | John | 35 | 2010-11-01 | 2010-12-05 | 2010-11-25 | 25 | C | 10 | Pending
Project-42 | Atul | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Project-43 | Jitender | 30 | 2010-11-01 | 2010-11-30 | 2010-11-19 | 19 | D | 11 | Too Late
Project-44 | Rajneesh | 25 | 2010-11-01 | 2010-11-25 | 2010-11-25 | 25 | A | 0 | Completed
Project-45 | Rashi | 25 | 2010-11-01 | 2010-11-25 | 2010-11-19 | 19 | C | 6 | Pending
Project-46 | Tarushikha | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-47 | Papori | 25 | 2010-11-01 | 2010-11-25 | 2010-11-20 | 20 | B | 5 | Under Process
Project-48 | Rana | 25 | 2010-11-01 | 2010-11-25 | 2010-11-19 | 19 | C | 6 | Pending
Project-49 | Faizal | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process
Project-50 | Sunny | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late
Formulas:
End Date = +[Start Date]+[Total Days]-1

## Status Check Sheet
Check the Status from Here |  |  |  | Completed |  |  |  | Drop Down Status from Here
Project | Team | Total Days | Start Date | End Date | Report Received | Activity Days | Rank | Remaing Report | Status | Helper Column
Project-11 | Rekha | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late | 11 | Completed
Project-17 | Meghna | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late | 17 | Under Process
Project-21 | Nagesh | 35 | 2010-11-01 | 2010-12-05 | 2010-11-25 | 25 | C | 10 | Pending | 21 | Pending
Project-26 | Karunakar | 30 | 2010-11-01 | 2010-11-30 | 2010-11-15 | 15 | D | 15 | Too Late | 26 | Too Late
Project-29 | Rizvi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-19 | 19 | D | 11 | Too Late | 29
Project-30 | Sanjana | 45 | 2010-11-01 | 2010-12-15 | 2010-11-25 | 25 | D | 20 | Too Late | 30
Project-36 | Omi | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process | 36
Project-46 | Tarushikha | 30 | 2010-11-01 | 2010-11-30 | 2010-11-25 | 25 | B | 5 | Under Process | 46
Formulas:
Start Date = +IF(ISNUMBER([Helper Column]),INDEX(Master!$E3:E52,[Helper Column],1),"")
Completed = +IF(ISNUMBER([Helper Column]),INDEX(Master!$F3:F52,[Helper Column],1),"")
Report Received = +IF(ISNUMBER([Helper Column]),INDEX(Master!$G3:G52,[Helper Column],1),"")
Hi Experts,
if i check my status from master sheet for knowing how many projects are under process, when i select the status from the drop down list, why dont all releated figures comes out. e.g. if i select under process all the under process project details shuold comes in rest of the detail area but it is not happening, please help me out.
Thanks - ROHAN