## Sheet4
Data
Divison | DIVISION | ProjectName | ABS Variance | Planned Duration Variance | Variance
DIV 1 | DIV 1 | Project 1 | 4 | 61 | 0.065574
DIV 1 |  | Project 2 | 16 | 34 | 0.47059
DIV 2 | DIV 2 | Project 1 | 13 | 21 | 0.61905

## Sheet6
Data
DIVISION | Sum of Variance(ABS) | Sum of Planned Duration | variance
DIV 1 | 20 | 95 | 0.21053
DIV 2 | 13 | 21 | 0.61905

## Sheet1
DIVISION | ProjectName | Activity_Name | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Variance(ABS) | Planned Duration
DIV 1 | Project 1 | Activity 1 | 2008-03-24 | 2008-03-28 | 2008-03-26 | 2008-03-26 | 2 | 5
DIV 1 | Project 1 | Activity 2 | 2007-06-29 | 2007-07-05 | 2007-06-29 | 2007-07-05 | 0 | 7
DIV 1 | Project 1 | . | 2007-06-14 | 2007-06-18 | 2007-06-14 | 2007-06-18 | 0 | 5
DIV 1 | Project 1 | . | 2007-06-29 | 2007-07-05 | 2007-06-29 | 2007-07-05 | 0 | 7
DIV 1 | Project 1 | . | 2007-06-01 | 2007-06-18 | 2007-06-01 | 2007-06-18 | 0 | 18
DIV 1 | Project 1 |  | 2007-07-13 | 2007-07-13 | 2007-07-13 | 2007-07-13 | 0 | 1
DIV 1 | Project 1 |  | 2007-09-12 | 2007-09-13 | 2007-09-12 | 2007-09-13 | 0 | 2
DIV 1 | Project 1 |  | 2007-11-01 | 2007-11-02 | 2007-11-01 | 2007-11-02 | 0 | 2
DIV 1 | Project 1 |  | 2008-01-01 | 2008-01-02 | 2008-01-01 | 2008-01-02 | 0 | 2
DIV 1 | Project 1 |  | 2008-02-25 | 2008-02-26 | 2008-02-25 | 2008-02-26 | 0 | 2
DIV 1 | Project 1 |  | 2007-06-14 | 2007-06-18 | 2007-06-14 | 2007-06-18 | 0 | 5
DIV 1 | Project 1 | Activity n | 2008-03-24 | 2008-03-28 | 2008-03-26 | 2008-03-26 | 2 | 5
DIV 1 | Project 2 | Activity 1 | 2008-01-22 | 2008-02-07 | 2008-01-22 | 2008-01-28 | 10 | 17
DIV 1 | Project 2 | Activity 2 | 2008-01-18 | 2008-01-18 | 2008-01-18 | 2008-01-18 | 0 | 1
DIV 1 | Project 2 | . | 2007-12-11 | 2007-12-11 | 2007-12-11 | 2007-12-11 | 0 | 1
DIV 1 | Project 2 | . | 2008-01-21 | 2008-01-23 | 2008-01-24 | 2008-01-29 | 6 | 3
DIV 1 | Project 2 | . | 2008-01-18 | 2008-01-18 | 2008-01-18 | 2008-01-18 | 0 | 1
DIV 1 | Project 2 | Activity n | 2008-03-21 | 2008-03-31 | 2008-03-21 | 2008-03-31 | 0 | 11
DIV 2 | Project 1 | Activity 1 | 2008-01-22 | 2008-02-08 | 2008-01-22 | 2008-01-28 | 11 | 18
DIV 2 | Project 1 | Activity 2 | 2008-03-10 | 2008-03-12 | 2008-03-10 | 2008-03-10 | 2 | 3